Literacy Action Plan 2019-2020

Vision: To embed the teaching of, and importance of, literacy throughout the curriculum to improve the academic outcomes for all students

| Strategy Description | Who? | Date to begin | Date due | Resources required | Desired outcome | Evaluation |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Prioritise ‘disciplinary literacy’ across the curriculum - Conduct subject literacy audits to see what literacy requirements are needed in each curriculum area - Subject areas to create a literacy plan and to assess current reading material - Audit staff and student attitudes towards literacy and evaluate current literacy provision | - KV/PLs - PLs - KV | Jan | Mar | - Provide PLs with audit sheet and helpful questions - Provide template to ensure consistency - SurveyMonkey | - All departments to prioritise and focus on Literacy - Subject Literacy Plans made throughout the curriculum, to be monitored for implementation and impact | - Literacy audits given to reps to be filled out within depts. |
| 2. Provide targeted vocabulary instruction in every subject - Create KOs for each topic in each subject, link to H/W and bell work - Train staff on etymology and morphology - Provide dictionaries in the classroom - Explicit teaching of Tier 2 vocab, with vocab posters in classrooms | - PLs - KV - KV -Teacher | Jan | Apr | - Provide KO template - KV to arrange training session - Provide tier 2 vocab lists and poster templates | - For students to become more confident in using key vocab - Staff and students have better understanding of key terms - Increased focus on using key vocab | - Pricing up dictionaries for every classroom |
| 3. Develop students’ ability to read complex academic texts - Staff training on how to teach reading in their subject - Reading models including ‘reciprocal reading’ 4. Break down complex writing tasks - Subjects to create writing frames for extended writing tasks that include sentence starters, reminder of Tier 2 vocabulary and teacher modelling | - KV - KV - PLs | Jan Jan | Apr Apr | - KV to arrange training session - Share different reading models, teachers to decide best model - Provide an example ready for subjects to personalise | - Create subject experts in literacy - Students engage more from reading activities - Students perform better in extended writing tasks |  |
| 5. Combine writing instruction with reading in every subject - Spelling should be actively taught, rather than simply tested - Pre teach challenging spellings of key terms - Subject areas to plan complementary reading and writing tasks | - PLs - Teacher - PLs | Jan | Apr | - KV to provide training on spelling strategies | - Writing and reading skills improve |  |
| 6. Provide opportunities for structured talk - Subject areas to actively plan for talking activities - Staff provided with various models on structuring talk, subject areas choose which is best for their area | - PLs - KV PLs | Jan | Apr | - Provide staff with models | - Writing and Reading Skills are improved as a result | - Tutor Reading discussion cards launched, to now be rolled out across subjects |
| 7. Provide high quality literacy interventions for struggling students - Reading log intervention for weakest 30 in each year group based on NGRT - EAL Tutor Reading group - Students extracted to the Hub - Monitor impact - New Pupil Premium focus - Year 6 Feeder school intervention 8. Create Department Literacy Reps/Champions - Each subject area to have a designated member of staff responsible for literacy - To support their department in delivering key literacy initiatives - To create subject specific literacy resources - To identify the literacy needs in that subject - Meet at least termly with KV | - KV - PS - JL - KV - KV - Reps - KV | Sep Oct | Ongoing Ongoing | - NGRT data from Jo - EAL specific texts - Lexia/Hegarty - Access to primary reading age data - Provide template for writing department literacy policy | - Students make significant progress - Subject Learning Walks to show improved focus on Literacy - students make significant progress | - Reading Logs went out and will be monitored in library lessons. NGRT in March will evaluate impact - All Literacy reps now named (ex. Science), first meeting planned before half term |
| 9. Structure Library lessons to maximise impact - Introduce new lesson plans for the library after seeing best practice in other schools - Make English staff more accountable in following Library lesson expectations - Track meaningful conversations with target students and log on tracker to show student progress - Increase parental engagement with students’ reading | - KV/DS - Eng | Oct | Ongoing | - Provide lesson plan for teachers, explaining potential impact - Conduct learning walks to ensure staff following expectations - Create tracking document for logging conversations and monitor - Staff survey before/after | - lessons more structured and progress is made - all staff follow expectations and meaningful conversations allow those students to make significant progress - Survey to demonstrate increased parental engagement linked to increased reading age | - New library lesson structure has been shared and implemented - Live 365 document being used to track student reading with a PP focus - Reading Logs require parental signature |
| 10. Increase profile of Literacy as a whole school driver/priority - Introduce Word of the Week tannoy so whole school community are encouraged to take part (WOTW linked to Character) - Literacy Bulletin emailed fortnightly with key foci and staff invited to share best practice | - KV/CA - KV | Sep | Ongoing | - Word of the Week promoted on SWAY - Bulletin provided with reading material | - Staff referring to WOTW and students using it in their work - all staff more heavily focussed on Literacy, shown through improved CUPS marking in student work and increased vocabulary | - Tannoy launched but with some lack of consistency due to exams - Bulletin reformed based on staff feedback |